## Sheet1
Feature | Priority (1-5) | Owner | Time Estimate (hrs) | Goal (date) | First Step | Status | Obstacles | Notes
Characters
Eat Bugs (see tongue) | 1 | Bex | 2 hrs | 2018-05-01 |  | Done
Score increase when eat bugs | 1 | Bex | 1 hr | 2018-05-03 |  | Done
Jump | 4 |  | 1 hr | 2018-05-04 |  | To do
Mosquitoes | 1 | Chella | 1 hr | 2018-04-29 |  | Done
Other Bugs | 1 | Chella | 5 hrs | 2018-04-29 |  | Done
Animation: UI
score counter change w/ color splash | 3 | Bex | 2 hrs | 2018-05-08 |  | Done
Animation: In World
Tongue Eats (scaling) | 1 | Bex | 1 hr | 2018-05-01 |  | Done
Bugs Move Around | 2 | Bex | 1 hr | 2018-05-04 |  | Done
Environment
Swamp Grass | 2 | Chella | .5 hr | 2018-05-04 |  | Done
Dead Log | 2 | Chella | .5 hr | 2018-05-04 |  | Done
Tree Trunks | 2 | Chella | .5 hr | 2018-05-04 |  | Done
Lily Pads | 2 | Chella | .5 hr | 2018-05-04 |  | Done
Sky | 1 | Tiga | 20 min | 2018-05-01 |  | Done
Audio: SFX
Bug Sounds | 1 | Tiga | 10 min | 2018-05-01 |  | Done
Tongue Sound | 1 | Tiga | 5 min | 2018-05-01 |  | Done
Jump Sound | 4 | Tiga | 5 min | 2018-05-01 |  | To do
Audio on any buttons | 1 | Tiga | 5 min | 2018-05-01 |  | Done
Audio: Music
Main Theme | 1 | Tiga | 10 min | 2018-05-03 |  | Done
Main Theme: Lost (downpitch) | 2 | Tiga | 5 min | 2018-05-08 |  | To do
Main Theme: Win (bouncier) | 2 | Tiga | 5 min | 2018-05-08 |  | To do
Feedback
Filter(?) when eat not good bug | 4 | Bex | 1 hr | 2018-05-08 |  | To do
UI
Score Counter | 1 | Bex | .5 hr | 2018-05-03 |  | Done
Title | 1 | Chella | 1 hr | 2018-05-03 |  | Done
Start Screen: Help | 1 | Chella | 1 hr | 2018-05-03 |  | Done
End Screen: Lose | 1 | Chella | 1 hr | 2018-05-03 |  | To do
End Screen: Win | 1 | Chella | 1 hr | 2018-05-03 |  | To do
Project Due Date: May 10, 2018
Categorize Features: |  |  | 3 hrs/day / 3 of us:
Characters |  |  | 1 hr/day per teammate
Environment
UI |  |  | Commit Hours:
Animation: UI and In world |  |  | Tiga - 18hr
Feedback |  |  | Bex-15/18 hrs
Audio: Music and SFX |  |  | Chella-13 hrs